## Slide 1
PROJECT HEALTH MONTHLY SYNTHESIS
Executive Client Delivery & Portfolio Status Dashboard
Report Date: July 2026 Reporting Cycle | 2 Projects Analyzed

## Slide 2
PORTFOLIO PERFORMANCE SYNTHESIS
Executive Summary & Portfolio Health
Zycus Professional Services PMO | Confidential
Slide 2
PORTFOLIO HEALTH SCORES
Green Status (Healthy)
0 Projects
Amber Status (Moderate Risk)
1 Project
Red Status (Critical Intervention Required)
1 Project
PORTFOLIO LEADERSHIP TAKEAWAYS
• 1 of 2 projects are behind schedule. Project Plan B has the largest schedule variance at 14.8%.
• The portfolio contains 73 active blockers and 10 overdue milestones requiring delivery follow-up.
• Input quality needs attention: 12 data-quality notes were recorded across the analyzed plans.
• Current portfolio distribution is Red: 1, Amber: 1, Green: 0.

## Slide 3
PORTFOLIO PERFORMANCE SYNTHESIS
Portfolio Status Overview
Zycus Professional Services PMO | Confidential
Slide 3
Project Name | Project Manager | RAG Status | % Complete | Schedule Health | Key Risk / Blocker
PROJECT PLAN B | Rajat Bothra | Red | 44.0% | Slippage: 14.8% | Zycus - UniSan S2P Implementation
S2P PROJECT | Aftab Hashambhai | Amber | 71.0% | Slippage: -14.1% | Configuration and Build phase

## Slide 4
PORTFOLIO PERFORMANCE SYNTHESIS
Schedule and Milestone Trends
Zycus Professional Services PMO | Confidential
Slide 4
PROJECT PLAN B PROGRESS DETAIL
● **Completion Progress**: 44.0% physical complete vs 58.8% elapsed timeline.
● **Overdue Milestones**: 2 overdue milestones logged in the active schedule.
● **Tasks In Progress**: 42 subtasks in active development.
● **Tasks Not Started**: 192 subtasks queued for subsequent phases.
● **On Hold Tasks**: 0 tasks flagged as on-hold.
S2P PROJECT PROGRESS DETAIL
● **Completion Progress**: 71.0% physical complete vs 56.9% elapsed timeline.
● **Overdue Milestones**: 8 overdue milestones logged in the active schedule.
● **Tasks In Progress**: 22 subtasks in active development.
● **Tasks Not Started**: 197 subtasks queued for subsequent phases.
● **On Hold Tasks**: 3 tasks flagged as on-hold.

## Slide 5
PORTFOLIO PERFORMANCE SYNTHESIS
Emerging Portfolio Risks & Blocker Analysis
Zycus Professional Services PMO | Confidential
Slide 5
THEME 1: DELIVERY EXECUTION PRESSURE
Active blockers are concentrated in Project Plan B (42), S2P Project (31). Overdue milestones are concentrated in S2P Project (8), Project Plan B (2). These items should drive the next PMO review and recovery plan.
THEME 2: REPORTING AND STAKEHOLDER SIGNALS
The plans contain 5 negative comment signal(s) and 12 data-quality warning(s). Validate owners, dates, statuses, and client dependencies before the next reporting cycle.

## Slide 6
PORTFOLIO PERFORMANCE SYNTHESIS
Strategic PMO Recommendations
Zycus Professional Services PMO | Confidential
Slide 6
ACTION 01
CONTAIN THE LARGEST BLOCKER CLUSTER
Run a focused recovery session for Project Plan B (42 active blockers), with an owner and target date for each critical item.
ACTION 02
RECOVER OVERDUE MILESTONES
Rebaseline the overdue milestone path for S2P Project (8 overdue milestones) and escalate dependencies that cannot be resolved this week.
ACTION 03
IMPROVE INPUT QUALITY
Close 12 data-quality warning(s) before the next cycle so leadership decisions are based on complete dates, statuses, and comments.

## Slide 7
NEXT STEPS & ROADMAP TO GREEN
1. Initiate Weekly Monitoring Cadence using the Reporting Agent
2. Conduct Data Completeness audits on incoming sheets (ensure baseline start/finish columns)
3. Review the recovery plan for Project Plan B (42 active blockers)
Source: Current weekly project health reports | Prepared for PMO review