## Slide 1
WEEKLY PROJECT HEALTH
Project Plan B
Project Manager: Rajat Bothra | Report date: 2026-07-02
RED STATUS
This deck explains the calculated RAG status and the actions that should follow from it.

## Slide 2
WEEKLY PROJECT HEALTH REPORT
The project is currently in a RED state
Status is based on the current schedule, milestones, blockers, and project-plan data.
RAG STATUS
RED
Calculated score: 56.0%
Project Plan B is currently at 44% completion with 58.75% time elapsed. The project is 14.75% behind schedule, and the SPI (Schedule P…
Overall progress
44.0%
Timeline elapsed
58.8%
Schedule slippage
14.8%
Active blockers
42
Overdue milestones
2
Project stage
Training Phase I
Zycus Professional Services PMO | Weekly reporting agent
2 / 4

## Slide 3
WEEKLY PROJECT HEALTH REPORT
Why this status was assigned
Plain-English reasoning based on schedule, milestones, blockers, and available project-plan signals.
STATUS EXPLANATION
The calculated RAG status is Red due to the following metrics: - Schedule Slippage: 14.75% - SPI: 74.89% - Overdue Tasks: 25 - Overdue Milestones: 2 - Blockers: 42 - Data Quality Assumptions: The summary sheet cells for Target Start Date, Target End Date, Schedule Delta, and Schedule Variance were unparseable Excel formulas, resulting in empty values.
WHAT THIS MEANS
Escalate the critical blockers and confirm a named owner, decision, and due date.
Use the next weekly review to confirm ownership, unblock decisions, and recovery dates.
Zycus Professional Services PMO | Weekly reporting agent
3 / 4

## Slide 4
WEEKLY PROJECT HEALTH REPORT
Risk drivers and recommended actions
Priorities for the next reporting cycle, with assumptions called out explicitly.
TOP RISK DRIVERS
• Blocker: Zycus - UniSan S2P Implementation
• Blocker: Training Phase I
• Blocker: Train The Trainer
• Overdue milestone: Training Phase I
• Overdue milestone: Train The Trainer
RECOMMENDED ACTIONS
• Escalate the critical blockers and confirm a named owner, decision, and due date.
• Run a recovery review for the overdue milestone and its delivery dependencies.
• Re-baseline the plan only after recovery dates and client dependencies are confirmed.
Data quality and assumptions
The summary sheet cells for Target Start Date, Target End Date, Schedule Delta, and Schedule V…
Zycus Professional Services PMO | Weekly reporting agent
4 / 4