PROJECT HEALTH REPORTING

RAG Methodology Framework  |  Auditable project-health classification for Professional Services

DESIGN PRINCIPLE The RAG outcome is deterministic: fixed rules and math create a reproducible 0-100 score. AI may only summarize evidence; it cannot choose or alter a color.

1. WEIGHTED HEALTH SCORE

Project Health Score = 0.30S + 0.25M + 0.20B + 0.10C + 0.10E + 0.05D  (0-100; higher is healthier)

| Signal | Weight | Deterministic rule / scoring bands |
| --- | --- | --- |
| S Schedule health | 30% | Slippage = time elapsed % - overall % complete. 100 if <=5%; 50 if >5-15%; 0 if >15%. |
| M Milestones | 25% | 100: none overdue; 80: 1-2 or <=5%; 50: 3-5 or <=15%; 30: >5 and >15%. Overdue = past end date and not Completed. |
| B Risks / blockers | 20% | 100: 0; 80: <=3 or <=3% of tasks; 50: <=10 or <=6%; 30: >10 and >6%. Includes active blockers / on-hold tasks. |
| C Budget proxy | 10% | SPI = overall % complete / time elapsed %. 100 if >=0.95; 50 if 0.80-0.94; 0 if <0.80. If unavailable (e.g., elapsed time = 0), default 100. |
| E Sentiment | 10% | Negative comment keywords: 100 none; 80 for 1-2; 65 for 3-5; 50 for 6-10; 30 for >10. Keywords include delay, blocker, risk, issue, dependency, on hold, escalate. |
| D Data quality | 5% | Start at 100; deduct 20 missing Summary, 10 missing Comments, 5 per unparseable date, and 15 missing core plan columns. Fall back to baseline / parent schedules. |

2. PORTFOLIO CLASSIFICATION & GOVERNANCE

RAG mapping: 80-100 GREEN (normal tracking)   60-79 AMBER (weekly mitigation)   <60 RED (executive intervention)

Summary status sync: Summary = Red/Critical forces Red. Summary = Yellow/Amber can downgrade a calculated Green to Amber.

Severe slippage: slippage >25% forces Red.

High blocker: force Red only when blockers >=15, blockers >=10% of tasks, and slippage is positive (>5%).

3. WHY RULES FIRST, LLM SECOND

Repeatable & auditable. Every color traces to the same inputs, thresholds, and calculations (for example, 14.7% slippage and four blockers), at local-rule speed and cost.

Explanation layer only. Local Qwen3.5-0.8B (Q4_K_M GGUF, cached under .models/) polishes quantitative write-ups; Gemini is optional. If inference is unavailable, the deterministic explanation is used. Neither provider can alter RAG.