## Slide 1
WEEKLY PROJECT HEALTH
S2P Project
Project manager: Aftab Hashambhai • Report date: 2026-07-02
AMBER STATUS
The project is 14.1% ahead of plan, but open delivery risks still require attention.
Current stage: Configuration and Build phase

## Slide 2
WEEKLY PROJECT HEALTH REPORT
Delivery risks need active management
The RAG status is based on project-plan progress, schedule, milestones, and blockers.
Prepared from the current project plan | 2 / 3
OVERALL PROGRESS
71.0%
TIMELINE ELAPSED
56.9%
SCHEDULE VARIANCE
-14.1%
ACTIVE BLOCKERS
31
Schedule:
71.0% complete vs 56.9% elapsed — 14.1% ahead of the planned pace.
Blockers:
31 active blockers, led by Configuration and Build phase and Functional Confuguration on Staging System/ Setup.
Milestones:
8 overdue milestones, including Configuration and Build phase and Functional Confuguration on Staging System/ Setup.

## Slide 3
WEEKLY PROJECT HEALTH REPORT
Actions to take before the next weekly update
Focus the delivery discussion on ownership, unblock decisions, and recovery dates.
Prepared from the current project plan | 3 / 3
1
Assign owners and dates for Configuration and Build phase and its open dependencies.
2
Hold a working session to unblock Configuration and Build phase.
3
Review resourcing and validate the recovery plan before the next weekly update.
Data note
6 data-quality note(s) were recorded; formula-based summary fields were treated as unavailable and task-level schedule data was used.